PROJECT PLAN:

LA RAZA

GENERAL HOSPITAL

MEXICO CITY

SEPTEMBER 2017

Number of patients per month: 3000

Stroke patients per month: 25/70 % ischemic stroke

Thrombolysis rate: 0%

ACUTE NETWORKS STRIVING FOR EXCELLENCE IN STROKE

CONTENT

| 1 | Justification |
| --- | --- |
| 2 | Objectives |
|  | 2.1 General objective |
|  | 2.2 Specific objectives |
| 3 | Background |
|  | 3.1 Initiative presentation |
|  | 3.2 Emergency room walkthrough |
|  | 3.3 Observation phase |
|  | 3.4 Project alignment with head of the ER |
|  | 3.5 Simulation with dummy patient |
| 4 | Infrastructure description (Facilities) |
| 5 | Human resources description (Staff) |
| 6 | Windows of opportunity detected |
| 7 | Critical path of stroke patients in La Raza General Hospital |
| 8 | Training program |
| 9 | Implementation time frame |
| 10 | Follow-up plan |
| 11 | Conclusions |
| 12 | Glossary |
| 13 | Appendices and references http://emedicine.medscape.com/article/1162677-overview |

- JUSTIFICATION

000

Stroke is one of the main causes of mortality and morbidity in Mexico and worldwide. According to the World Health Organization, 1 in 6 people will suffer an event of stroke and every 30 minutes a person will die from the same reason. Particularly Mexico City, due to the increasingly large amount of population with stroke risk factors, is a critical city for optimizing stroke care in emergency units. La Raza General Hospital is an institution with the necessary infrastructure to develop an efficient program for optimizing stroke patient care and to build a stroke network.

2. OBJECTIVES

2.1 General Objective

To guide La Raza General Hospital’s emergency room into the conformation of a stroke unit by means of implementing a project plan for optimizing stroke patients’ timely management.

2.2  Specific Objectives and Expected Results

- Present ANGELS initiative both to the operational area and to the administrative area of La Raza General Hospital and to define the date of kick off.

- Work the institutional diagnosis of La Raza General Hospital through the hospital’s human and material resources information.

  - To perform an observation phase of the patient care flow in the emergency room.

  - To perform a simulation with a dummy patient that allows measuring the current times and to establish objectives and goals.

- Define a Project plan in collaboration with Dr. Miguel Russi, chief of emergency services.

- Train all the personnel involved in stroke patient care.

- Reduce attention times in each link of the attention chain of stroke patients (door-to-physician, door-to-imaging, door-to-interpratation, door-to-needle).

- Increase thrombolysis rate >5% of overall ischaemic strokes.

- Reduce disability and mortality rates in La Raza General Hospital.

- To provide clinical follow-up recommendations for post-thrombolysis and discharge.

- Keep constant follow-up of the established stroke team for a correct monitoring of the implemented process.

- Transform La Raza General Hospital into a reference stroke centre in Mexico City.

3. BACKGROUND

3.1  ANGELS Initiative Presentation

It took place on June 15th, 2017.

3.2  Emergency Room Walkthrough

It took place on June 22nd, 2017.

We perform a registry of the hospital’s human and material resources to attend stroke patients in the visited areas, which include:

- Emergency room main entrance

- Triage

- Cubicles

- Observation área

- Trauma room

- Imaging room

3.3  Observation Phase

It took place on June 23rd, 2017.

| BARRIERS |  | RECOMMENDATIONS |
| --- | --- | --- |
| Triage doctors do not perform Cincinatti scale to patients with sudden neurological deficit. |  | Training in the cardinal signs and symptoms of stroke patients (Cincinatti Scale) and the importance of timely management. |
| Attending physicians and residents do not know clinical scales, as well as the initial strategies to perform in stroke patients. |  | Cincinatti scale training Training in stroke patient care and the importance of giving priority to certain action |
| Ignorance of NIHSS for the adequate assessment of stroke patients. |  | Training and certification in the NIHSS for all the medical staff. |
| Ignorance of prognostic scores, such as DRAGON, SEDAN, HAT or ASPECTS. |  | Training in prognostic scores. |
| Fail to identify radiological signs during the hyperacute and acute stages. |  | Training in stroke radiology. |
| Inability to establish a flowing process in acute stroke patient care. |  | Establish a flow chart to improve stroke patient care. Establish interdepartmental agreements to improve stroke patient care. |

The flow of attention of the patients who come to the emergency area was observed, from their entrance through the main door of the hospital’s emergency room.

When entering the hospital, the patient went to an admission desk where it was assigned a color depending on the reason for attention. The patient waited his turn depending on the color of the assigned until he was called by the triage doctor. The waiting time usually fluctuates around 10 minutes.

Once entering triage, he was assessed by a doctor, where another severity color is assigned, where it took an average of 5 minutes for taking vital signs, rapid interrogation and rapid physical examination. He did not perform any stroke scale, however, he recognized the sudden focal neurological deficit as an emergency and passed the patient to the trauma room.

When the patient was identified with probable stroke, was admitted to the emergency room where the ER resident performed a neurological assessment, without performing the NIHSS. He ordered laboratory tests and referred the patient to the CT scanner, however the patient waited almost 60 minutes to be admitted to the CT Scan room in the 2nd floor of the hospital. It took another 15 minutes to receive an interpretation of the CT scan. The patient returned to trauma room where contraindications were interrogated and thrombolysis was performed.

3.4  Project Plan Alignment with the Chief of Emergency Services

It took place July 14th 2017.

3.5  Simulation With Dummy Patient

It took place July 12th 2017.

| PARAMETER |  | TIME (MINUTES) |  | OBSERVATIONS |
| --- | --- | --- | --- | --- |
| Door-to- physician |  | 1min |  | They order lab tests |
| Door-to-stroke team |  | NA |  | They wait for confirmation |
| Door-to-CT |  | 64 min |  | Waited almost an hour for CT |
| Door-to-interpretation |  | 82 min |  | Almost 20 minutes |
| Door-to- Needle |  | No alteplase |  |  |

4. MATERIAL RESOURCES DESCRIPTION (FACILITIES)

Refer to Quick format.

5. HUMAN RESOURCES DESCRIPTION (STAFF)

Refer to Quick format.

6. WINDOWS OF OPPORTUNITY DETECTED

Security Staff

- All shifts should be trained in the symptoms and signs of stroke in order to facilitate access of patients with stroke

- To provide an alarm or radio communication to inform the arrival of a probable stroke patient.

Triage Staff

- Train and update doctors and nurses to identify matching signs of stroke.

- Remind the importance of vital signs, weight and height (especially weight, whenever it can be possible).

- Do not delay time with double history and examination from doctors and nurses.

Nursing Staff

- Include nursing students and acting nurses in the training sessions.

- Train nursing staff in the identification of stroke patients.

- Critic actions on first contact:

  - Vital signs

  - Glucose

- General arrangements of critic patients in the ER

- Drug calculation, preparation and administration.

- Patient care before and after thrombolysis

- Provide protocols and checklists in paper

- Provide electronic protocols and checklists: Thrombolyse app

- Monthly meetings with nursing staff for feedback

Laboratory Staff

- Priority tests.

- Fast results delivery.

- Maximum priority to acute stroke patients on window time.

Personal Médico en Urgencias

- Involve all the medical staff (attending physicians, residents, and interns) in the identification of stroke patients.

- To know diagnostic scales and prognostic scores (NIHSS, CINCINATTI, DRAGON, SEDAN) and certify all the medical staff in NIHSS.

- To define the timing for scales, essential lab tests and their importance.

- To train all the staff in the identification of bleed and early signs in the CT scan for a correct diagnosis and decision making.

- Surveillance of neurological improvement or deterioration according to stroke guidelines.

- To know exclusion criteria for thrombolysis, and to establish clinical follow-up protocols during the next 24 hours.

- Provide protocols and checklists in paper

- Provide electronic protocols and checklists: Thrombolyse app

- Keep a registry of stroke patients admitted to the ER.

- Monthly meetings with nursing medical staff for feedback

Radiology Staff

- Involve the chief of radiology, residents, attending physicians in the promptly interpretation of early signs of stroke on CT and the ASPECTS.

- Establish agreement: Patients with a CT scan order marked as ”acute stroke on window time” have maximum priority over programmed patients.

7. ACCESS ROUTE OF STROKE PATIENTS

Constumized

Community

Secondary prevention

Rehabilitation

Caregivers

Secondary prevention

Stroke unit

Diagnosis and complications

Thrombolysis

Diagnosis

Transportation

Prehospital                         Hyperacute                        Multidisciplinary               Discharge Plan

8. TRAINING PROGRAM

The training program (appendix 2), was confirmed by the heads of emergency services, medical education, and the hospital directors with the following schedule.

| SUBJECT | DATE | SCHEDULE | PERSONNEL* | SHIFT** | SPEAKER |
| --- | --- | --- | --- | --- | --- |
| Stroke unit organization | OCTOBER-NOVEMBER | 8-13 hrs | T,N,E,O | M,N | Dr. Armando Sánchez Jordán |
| Evaluation and severity assesment | OCTOBER-NOVEMBER | 8-13 hrs | T,N,E,O | E,M | Dr. Armando Sánchez Jordán |
| Imaging | OCTOBER-NOVEMBER | 8-13 hrs | T,N,E,O | M,N | Dr. Armando Sánchez Jordán |
| Hyperacute management | OCTOBER-NOVEMBER | 8-13 hrs | T,N,E,O | E,M | Dr. Armando Sánchez Jordán |
| Secondary prevention | OCTOBER-NOVEMBER | 8-13 hrs | T,N,E,O | M,N | Dr. Armando Sánchez Jordán |
| Rehabilitation |  |  |  |  | Dr. Armando Sánchez Jordán |

*S: Security staff//  T: Triage //   N: Nursing staff //  E: Emergency room medical staff // I: Imaging staff. // O: Others: internists, rehab, etc

**M: morning, E: evening, N: Night

9.  IMPLEMENTATION TIME FRAME

A period of 6 months is estimated in order to be able to develop different strategies that gradually reflect an improvement in the standards of stroke patient care, as well as an increase in the thrombolysis rate.

This process has been approved by the emergency department, the medical education direction and the general direction of La Raza General Hospital.

10. FOLLOW-UP PLAN

A simulation with a dummy patient will be carried out on a monthly basis to record progress or improvements in the care of stroke patients, as well as to constantly detect windows of opportunity that will be strengthened in the day-to-day of the trainings.

Once the training has been completed for all the personnel involved, a simulation of a fictitious patient will be made, which will be compared in time and form with the first dummy patient performed on site, with the above, there will be an objective assessment of the door-to-needle time and the actions taken in the stroke patient care.

11. CONCLUSIONS

There are different organizations in the world that certify hospitals as stroke centers. One of the best is the Joint Commission, among others. This certification is granted to the programs or associated services in health care in the field of neurology or orthopedics. In the event that your hospital is eligible for this certification it could be recognized as: Hospital La Raza stroke ready center, according to whether the requirements of appendix 1 are met.

12. GLOSSARY

| CVD | Cerebrovascular disease. |
| --- | --- |
| Stroke unit | A stroke unit is a specialized and clearly defined hospital area where patients with stroke come in and receive the necessary care from a multidisciplinary team (doctors, nurses) who have knowledge, training and specific capabilities in the field of stroke with defined tasks and regular interaction with other disciplines. |
| Stroke unit goals | Minimize the volume of irreversible infarcted brain tissue. To avoid stroke recurrence. To prevent complications and to reduce disability. |
| Types of Units | Acute Stroke Ready Hospital Primary Stroke Center Comprehensive Stroke Center (appendix 1) |

| Appendix 1 | Types of stroke centers according to the Joint Commission |
| --- | --- |
| Appendix 2 | ANGELS Initiative training program |
| Appendix 3 | Differences among stroke centers. |
| Appendix 4 | Online information on creating stroke centers. Available at: http://emedicine.medscape.com/article/1162677-overview |

13. APPENDICES AND REFERENCES